# MatrixConf25 + c3voc
## Attending
- justjanne
- braid
- thib
- kim
- jwacalex
- hexchen
- derchris
- yan
## Meeting Minutes
### General Information
- Three Days Three Rooms/Track
  - Recording and Livestreaming
  - Event works with volunteers for all the stuff
  - During Buildup we need someone from the venue for Audio/Video/Network Setup
  === Shipping and Transportation
  - how early can we receive and how late can we return the equipment from location?
  - the venue can receive gear before the conference. we has to confirm how early.
  - someone has to be there to receive the package and check that everything is intact.
  - → matrixconf can ask the venue to inspect the packages, if there is something broken, the foundation must replace the parts
  - Thib to check with the venue if their insurance works for the hardware and hardware transportation (ADSp-Verzichterklärung)
  === Budget
  - VOC normally estimates a fixed amount for a day and room: 500€ → 3 tracks 3 days = 4500€
  - negotiable from VOC side
  - From Matrix side: Does 10k€ budget sound realistic for transport, accommodation, insurance, and 3 tracks 3 days?
  - hardware transport + transport insurance would be about 6000€
  - how to pay
    - the Chaos Computer Club Veranstaltungsgesellschaft mbH (CCCV) will invoice hardware and shipping
    - hotel is done by Matrix
    - person transport is done by ?
  - Assuming €130 per night, 6 rooms, and 5 nights (conference + 1 day before and 1 day after) that's about €4k
  - Then we also have to add the train on top of that: at least 1k in train ticket
  - Looking at a total budget about €15K
  === # of people
  - VOC: 1 can do a room but 2 are better
  - Volunteers will help with camera operation and video mixing
  === Venue
  - Videos of the venue: https://cloud.thibaultmart.in/s/8CWrEcMoETL5kkM
  - Network requirements: 1 uplink to connect the VOC equipment
  - Thib to ask if it is possible to create VLans on the organizers network
  === Volunteering
  - VOC would require 2 volunteers per talk to staff the camera and mixing
  - Doing 2 2hr shifts
  === Followup Meeting
  - Date: 2025-07-07 20:30 CEST (KW28)
  - Topics:
    - Number of Tracks
    - Funding
    - Number of VOC Volunteers