MatrixConf25 + c3voc Meeting 2

Attending

braid

derchris

sophie

thunfisch

jwacalex

Meeting Minutes

C3VOC Crew

enough members (even without those who wait for vacation)

Crew List: https://c3voc.de/wiki/events:matrix25

only necessary people, no unlimited budget. calculated with 6 to 8 people

VOC matrix IDs

@sophie:sophies-kitchen.eu

@derchris:matrix.org

Budget

Calculation / Budget is accepted (Worst Case Estimation 15.000 Eur)

Transportation

Venue is thinking about how to handle it

Number of Tracks

Three Tracks

Volunteers

Two volunteers per Slot / Lecture / whatever

No Backtoback Shifts

They need an introduction, there will be a slot on day 1 (unconference day)

Event Dates

arrival of crew on the 14th

first day (15th of october) is unconference and buildup

schedule for build-up

talks on the 16th, 17th and 18th

teardown on the 19th till 16:00

Design

https://c3voc.de/wiki/howto:design-artefakte
https://c3voc.de/wiki/requirements